## Executive Summary
INTEGRATED PLAN — EXECUTIVE SUMMARY
v6.0 ¦ 2026-06-09 14:52 ¦ coupled curing + building plan
Metric | Value
Plan version | v6.0
Run timestamp | 2026-06-09 14:51
Planning horizon (days) | 31
Coupling steps | 6
Original demand (tyres) | 718,128
Curing-only capacity | 692,024
Building-only capacity | 571,144
FEASIBLE plan (cured = built) | 563,932
vs demand | 78.5%
final curing planned | 563,932
final building built | 563,932
Binding constraint | Building (green-tyre supply)
Avg curing press util | 73.3%
Avg building machine util | 93.4%
Days building lags curing | 29 / 31
Building-limited SKUs | 60
Curing-limited SKUs | 16
Fully demand-met SKUs | 44

## SKU Reconciliation
PER-SKU RECONCILIATION (demand -> curing -> building)
v6.0 ¦ 2026-06-09 14:52 ¦ coupled curing + building plan
SKUCode | Priority | Demand | Curing_Capacity | Building_Capacity | Final_Cured | Final_Built | Gap_vs_Demand | Binding_Constraint
1325214813075SUNE1 | 0.1039 | 74580 | 74404 | 74580 | 74228 | 74228 | 352 | Curing-limited
1225170015012LSTL0 | 0.0696 | 65500 | 65576 | 65500 | 65576 | 65576 | 0 | Demand met
1D25212812074FXC10 | 0.0423 | 30360 | 30097 | 30360 | 29835 | 29835 | 525 | Curing-limited
1D25213812090FXPC0 | 0.0404 | 29040 | 28818 | 29040 | 28596 | 28596 | 444 | Curing-limited
1325214812074TUHL0 | 0.0376 | 27000 | 26936 | 27000 | 26872 | 26872 | 128 | Curing-limited
1D25215013008SXC11 | 0.0362 | 26000 | 26239 | 16533 | 16843 | 16843 | 9157 | Building-limited
1D25212812086FXPC0 | 0.0359 | 25800 | 26040 | 13672 | 8240 | 8240 | 17560 | Building-limited
1325114812074TUHL0 | 0.0279 | 20000 | 20000 | 1 | 2 | 2 | 19998 | Building-limited
1325221715100SRHT0 | 0.0265 | 19000 | 18881 | 19000 | 18771 | 18771 | 229 | Curing-limited
1325221417100HURL1 | 0.0237 | 17000 | 17000 | 17000 | 17000 | 17000 | 0 | Demand met
1325216814085STMX0 | 0.0195 | 14000 | 14002 | 14000 | 14002 | 14002 | 0 | Demand met
1325218515088HTMX0 | 0.0167 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | Demand met
1325219416089HRHE0 | 0.0167 | 17000 | 16955 | 17000 | 16911 | 16911 | 89 | Curing-limited
1325215813079SUHL0 | 0.0167 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | Demand met
1325119015008SRBT0 | 0.0167 | 12000 | 11970 | 12000 | 11940 | 11940 | 60 | Curing-limited
1325221416095VURL0 | 0.0167 | 12000 | 12000 | 12000 | 12000 | 12000 | 0 | Demand met
1325215813079STMX0 | 0.0139 | 10000 | 10000 | 10000 | 10000 | 10000 | 0 | Demand met
1325215613075TUHL0 | 0.0128 | 9200 | 9200 | 9200 | 9200 | 9200 | 0 | Demand met
1425118916008QRBT0 | 0.0125 | 9000 | 9000 | 9000 | 9000 | 9000 | 0 | Demand met
1325213615099MSXT0 | 0.0118 | 8500 | 8500 | 0 | 0 | 0 | 8500 | Building-limited
1225223516121PSKP0 | 0.0117 | 11420 | 11568 | 11420 | 11568 | 11568 | 0 | Demand met
1325223517104HRHT0 | 0.0111 | 8000 | 8000 | 8000 | 8000 | 8000 | 0 | Demand met
1325215513073TUHL0 | 0.0108 | 7747 | 7733 | 0 | 0 | 0 | 7747 | Building-limited
1225221715115SSTL0 | 0.0107 | 14167 | 14168 | 14167 | 14168 | 14168 | 0 | Demand met
1325219316087VUTR0 | 0.0097 | 7000 | 6942 | 7000 | 6886 | 6886 | 114 | Curing-limited
1325216614081STMX0 | 0.0092 | 6634 | 6619 | 6634 | 6605 | 6605 | 29 | Curing-limited
1325123715105SBRT0 | 0.0091 | 6500 | 6541 | 6500 | 6541 | 6541 | 0 | Demand met
1325217514082TTMX0 | 0.009 | 6492 | 6492 | 6492 | 6492 | 6492 | 0 | Demand met
1325220515094VUTR0 | 0.0085 | 6098 | 6050 | 6098 | 6002 | 6002 | 96 | Curing-limited
1325216814085SURL0 | 0.0085 | 6076 | 0 | 0 | 0 | 0 | 6076 | Building-limited
1325214612069TUHL0 | 0.0084 | 6000 | 6000 | 0 | 0 | 0 | 6000 | Building-limited
1325216614081SUTR0 | 0.0082 | 5866 | 5868 | 5866 | 5868 | 5868 | 0 | Demand met
1325119815106QBRQ0 | 0.0081 | 5889 | 5870 | 5889 | 5850 | 5850 | 39 | Curing-limited
1325217413077TUSP0 | 0.0079 | 5703 | 5704 | 5703 | 5704 | 5704 | 0 | Demand met
1225121715115SSTL0 | 0.0079 | 5668 | 5668 | 5668 | 5668 | 5668 | 0 | Demand met
1325216514079TTMX0 | 0.0074 | 5318 | 5318 | 5318 | 5318 | 5318 | 0 | Demand met
1225170015010LSTL0 | 0.0072 | 5200 | 5200 | 5200 | 5200 | 5200 | 0 | Demand met
1325216814085SUTR0 | 0.0072 | 5181 | 5140 | 5181 | 5098 | 5098 | 83 | Curing-limited
1325216814085TURL0 | 0.0071 | 5113 | 5114 | 5113 | 5114 | 5114 | 0 | Demand met
1325220516095HTMX0 | 0.007 | 5000 | 5000 | 5000 | 5000 | 5000 | 0 | Demand met
1325218515088HUTR0 | 0.0069 | 4924 | 4884 | 4924 | 4845 | 4845 | 79 | Curing-limited
1325121715115SLTB0 | 0.0066 | 4770 | 4770 | 4770 | 4770 | 4770 | 0 | Demand met
1325121715100SRBT0 | 0.0064 | 4569 | 4570 | 4569 | 4570 | 4570 | 0 | Demand met
1325215613075TTMX0 | 0.0059 | 4239 | 4240 | 4239 | 4240 | 4240 | 0 | Demand met
1325217613082TUNE0 | 0.0059 | 4202 | 4202 | 4202 | 4202 | 4202 | 0 | Demand met
1325216813083TUNE0 | 0.0056 | 4000 | 4000 | 0 | 0 | 0 | 4000 | Building-limited
1325121715100SBRT0 | 0.0056 | 4000 | 2756 | 69 | 70 | 70 | 3930 | Building-limited
1325221715100SRXT0 | 0.0056 | 4000 | 4000 | 0 | 0 | 0 | 4000 | Building-limited
1D25215Z13008QXPC0 | 0.0049 | 5148 | 5148 | 0 | 0 | 0 | 5148 | Building-limited
1325223715105SRXT0 | 0.0046 | 3274 | 3274 | 0 | 0 | 0 | 3274 | Building-limited
1325217514082TVECH | 0.0045 | 3200 | 3180 | 0 | 0 | 0 | 3200 | Building-limited
1325121715100SRXT0 | 0.0044 | 3188 | 3188 | 0 | 0 | 0 | 3188 | Building-limited
1325216513077TUHL0 | 0.0042 | 3005 | 3006 | 3005 | 3006 | 3006 | 0 | Demand met
1D25114012008QSTL0 | 0.0042 | 3000 | 268 | 0 | 0 | 0 | 3000 | Building-limited
1D25214012008QSTL0 | 0.0042 | 3000 | 0 | 0 | 0 | 0 | 3000 | Building-limited
1225219015010QSTL0 | 0.004 | 2900 | 2905 | 0 | 0 | 0 | 2900 | Building-limited
1325214813075STMX0 | 0.004 | 2900 | 2900 | 0 | 0 | 0 | 2900 | Building-limited
1325223616105HRHT0 | 0.004 | 2847 | 2848 | 0 | 0 | 0 | 2847 | Building-limited
1325217613082TUNE2 | 0.0036 | 2618 | 2620 | 0 | 0 | 0 | 2618 | Building-limited
1325217514082TUTR0 | 0.0035 | 2515 | 2516 | 0 | 0 | 0 | 2515 | Building-limited
1325223418103HRHP0 | 0.0035 | 2500 | 0 | 0 | 0 | 0 | 2500 | Building-limited
1325218416086VURL0 | 0.0035 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | Demand met
1325218514086HURL0 | 0.0035 | 2500 | 2500 | 2500 | 2500 | 2500 | 0 | Demand met
1325222417099HURL0 | 0.0035 | 2500 | 2479 | 2500 | 2460 | 2460 | 40 | Curing-limited
1325217514082HURL2 | 0.0033 | 2362 | 2362 | 2362 | 2362 | 2362 | 0 | Demand met
1325218515088TURL0 | 0.003 | 2136 | 2136 | 2136 | 2136 | 2136 | 0 | Demand met
1325220316091VURL1 | 0.0028 | 2778 | 2778 | 2778 | 2778 | 2778 | 0 | Demand met
1325219415088VURL1 | 0.0028 | 2000 | 1984 | 2000 | 1968 | 1968 | 32 | Curing-limited
1325226517112HRHT0 | 0.0028 | 3325 | 3299 | 3325 | 3273 | 3273 | 52 | Curing-limited
1225121Z14112LSTL0 | 0.0025 | 1787 | 1782 | 0 | 0 | 0 | 1787 | Building-limited
1225119015010QSTL0 | 0.0024 | 1703 | 0 | 0 | 0 | 0 | 1703 | Building-limited
1325220516095HUTR0 | 0.0022 | 1586 | 1602 | 1586 | 1602 | 1602 | 0 | Demand met
1325218415084TTMX0 | 0.0022 | 1557 | 1558 | 0 | 0 | 0 | 1557 | Building-limited
1225121716010SXC10 | 0.0021 | 1991 | 1992 | 0 | 0 | 0 | 1991 | Building-limited
1325217415081HUTR0 | 0.0021 | 1524 | 1524 | 0 | 0 | 0 | 1524 | Building-limited
1D25115013008QXPC0 | 0.0021 | 1500 | 1500 | 0 | 0 | 0 | 1500 | Building-limited
1325218414082HUSP0 | 0.0019 | 1386 | 1386 | 0 | 0 | 0 | 1386 | Building-limited
1325217614084HURL1 | 0.0019 | 1379 | 1380 | 0 | 0 | 0 | 1379 | Building-limited
1225221716010SXC10 | 0.0018 | 1320 | 1320 | 0 | 0 | 0 | 1320 | Building-limited
1325218615089HURL0 | 0.0018 | 1314 | 1314 | 1314 | 1314 | 1314 | 0 | Demand met
1325217614084HURL2 | 0.0018 | 1295 | 1296 | 1295 | 1296 | 1296 | 0 | Demand met
1325217514086VURL0 | 0.0018 | 1273 | 0 | 0 | 0 | 0 | 1273 | Building-limited
1325223916120QRAB0 | 0.0015 | 1113 | 1114 | 0 | 0 | 0 | 1113 | Building-limited
1225222716121MXC11 | 0.0015 | 1079 | 0 | 0 | 0 | 0 | 1079 | Building-limited
1325218614088HURL0 | 0.0014 | 1034 | 1028 | 0 | 0 | 0 | 1034 | Building-limited
1325222117094YLEV0 | 0.0014 | 1003 | 0 | 0 | 0 | 0 | 1003 | Building-limited
1325216814085TURP0 | 0.0014 | 1000 | 0 | 0 | 0 | 0 | 1000 | Building-limited
1325219515091VZEP0 | 0.0013 | 951 | 0 | 951 | 952 | 952 | 0 | Demand met
1325218414086VURL0 | 0.0013 | 909 | 0 | 0 | 0 | 0 | 909 | Building-limited
1325220416092VURL0 | 0.0013 | 909 | 910 | 909 | 910 | 910 | 0 | Demand met
1325123715105SRXT0 | 0.0013 | 900 | 900 | 0 | 0 | 0 | 900 | Building-limited
1325213612065SULX1 | 0.001 | 752 | 752 | 0 | 0 | 0 | 752 | Building-limited
1225223516121RBVN0 | 0.001 | 711 | 0 | 0 | 0 | 0 | 711 | Building-limited
1325220515094VTMX0 | 0.0009 | 651 | 652 | 651 | 652 | 652 | 0 | Demand met
1225221615008QXC10 | 0.0009 | 615 | 616 | 0 | 0 | 0 | 615 | Building-limited
1325219316087VURP0 | 0.0008 | 609 | 610 | 609 | 610 | 610 | 0 | Demand met
1325223517104HRPG0 | 0.0008 | 579 | 580 | 579 | 580 | 580 | 0 | Demand met
1325220515094VZEP0 | 0.0008 | 558 | 0 | 558 | 558 | 558 | 0 | Demand met
1325220416092VURP0 | 0.0007 | 536 | 536 | 536 | 536 | 536 | 0 | Demand met
1325222317101VUX10 | 0.0006 | 456 | 456 | 284 | 284 | 284 | 172 | Building-limited
1325218515088HURP0 | 0.0006 | 456 | 456 | 0 | 0 | 0 | 456 | Building-limited
1325217514082HURP0 | 0.0006 | 421 | 422 | 421 | 422 | 422 | 0 | Demand met
1225219015008SLTB0 | 0.0005 | 346 | 12 | 0 | 0 | 0 | 346 | Building-limited
1325216814085TURS0 | 0.0004 | 300 | 300 | 0 | 0 | 0 | 300 | Building-limited
1325221416095VURS0 | 0.0004 | 300 | 300 | 0 | 0 | 0 | 300 | Building-limited
1D25214012006QXC10 | 0.0004 | 300 | 298 | 0 | 0 | 0 | 300 | Building-limited
1325218515088TURS0 | 0.0004 | 300 | 300 | 0 | 0 | 0 | 300 | Building-limited
1325221417100HURS0 | 0.0004 | 300 | 300 | 0 | 0 | 0 | 300 | Building-limited
1325216614081TVECE | 0.0004 | 290 | 0 | 0 | 0 | 0 | 290 | Building-limited
1325214613071TTMX0 | 0.0004 | 289 | 290 | 289 | 290 | 290 | 0 | Demand met
1225220Z16008RXC10 | 0.0003 | 242 | 242 | 0 | 0 | 0 | 242 | Building-limited
1225222716121NXC11 | 0.0003 | 200 | 0 | 0 | 0 | 0 | 200 | Building-limited
1325114613071TTMX0 | 0.0002 | 148 | 148 | 148 | 148 | 148 | 0 | Demand met
1325221317098VUX10 | 0.0001 | 102 | 102 | 0 | 0 | 0 | 102 | Building-limited
1225222615008RXC10 | 0.0001 | 93 | 94 | 0 | 0 | 0 | 93 | Building-limited
1325221217095YLEV0 | 0.0001 | 40 | 0 | 0 | 0 | 0 | 40 | Building-limited
1325222217098VUX10 | 0 | 26 | 26 | 0 | 0 | 0 | 26 | Building-limited
1325221117091YLEV0 | 0 | 20 | 0 | 0 | 0 | 0 | 20 | Building-limited
1325219515095VLHP0 | 0 | 12 | 0 | 0 | 0 | 0 | 12 | Building-limited
1325218614092VURL0 | 0 | 11 | 0 | 0 | 0 | 0 | 11 | Building-limited

## Daily Plan
DAILY PLAN — GTs BUILT vs CURED (cumulative)
v6.0 ¦ 2026-06-09 14:52 ¦ coupled curing + building plan
Date | Built_Today | Cured_Today | Cum_Built | Cum_Cured | Lead_Units | Status
2026-05-01 | 18888 | 24883 | 18888 | 24883 | -5995 | LAG
2026-05-02 | 18486 | 24815 | 37374 | 49698 | -12324 | LAG
2026-05-03 | 18554 | 24688 | 55928 | 74386 | -18458 | LAG
2026-05-04 | 18557 | 24808 | 74485 | 99194 | -24709 | LAG
2026-05-05 | 18549 | 24697 | 93034 | 123891 | -30857 | LAG
2026-05-06 | 18588 | 24294 | 111622 | 148185 | -36563 | LAG
2026-05-07 | 18746 | 22719 | 130368 | 170904 | -40536 | LAG
2026-05-08 | 18752 | 22264 | 149120 | 193168 | -44048 | LAG
2026-05-09 | 18746 | 22210 | 167866 | 215378 | -47512 | LAG
2026-05-10 | 18704 | 21934 | 186570 | 237312 | -50742 | LAG
2026-05-11 | 18602 | 22099 | 205172 | 259411 | -54239 | LAG
2026-05-12 | 18595 | 21919 | 223767 | 281330 | -57563 | LAG
2026-05-13 | 18600 | 21683 | 242367 | 303013 | -60646 | LAG
2026-05-14 | 18602 | 20320 | 260969 | 323333 | -62364 | LAG
2026-05-15 | 18597 | 19512 | 279566 | 342845 | -63279 | LAG
2026-05-16 | 18556 | 18326 | 298122 | 361171 | -63049 | LAG
2026-05-17 | 18546 | 17304 | 316668 | 378475 | -61807 | LAG
2026-05-18 | 18547 | 16798 | 335215 | 395273 | -60058 | LAG
2026-05-19 | 18548 | 15829 | 353763 | 411102 | -57339 | LAG
2026-05-20 | 18547 | 15345 | 372310 | 426447 | -54137 | LAG
2026-05-21 | 18548 | 15094 | 390858 | 441541 | -50683 | LAG
2026-05-22 | 18548 | 14898 | 409406 | 456439 | -47033 | LAG
2026-05-23 | 18547 | 14336 | 427953 | 470775 | -42822 | LAG
2026-05-24 | 18527 | 13833 | 446480 | 484608 | -38128 | LAG
2026-05-25 | 18344 | 13233 | 464824 | 497841 | -33017 | LAG
2026-05-26 | 18343 | 13194 | 483167 | 511035 | -27868 | LAG
2026-05-27 | 18343 | 12219 | 501510 | 523254 | -21744 | LAG
2026-05-28 | 18344 | 11780 | 519854 | 535034 | -15180 | LAG
2026-05-29 | 18344 | 11319 | 538198 | 546353 | -8155 | LAG
2026-05-30 | 17883 | 9263 | 556081 | 555616 | 465 | OK
2026-05-31 | 7851 | 8316 | 563932 | 563932 | 0 | OK

## Coupling Log
COUPLING STEPS (demand -> curing -> building envelope -> feasible)
v6.0 ¦ 2026-06-09 14:52 ¦ coupled curing + building plan
Step | Description | Tyres
1 Curing (full demand) | press/mould capacity | 692024
2 Building envelope | max GT supply / SKU | 571144
3 Curing (env-capped) | first feasible plan | 570528
4 Building JIT | real time-phased build | 564887
5 Curing (final) |  | 563932
6 Building (final) | final delivery | 563932